DOCUMENT #11 OF 13

PROJECT PLAN

ProjeX Suite

11 Phases · 48 Weeks · Resource Allocation · Milestones

| Field | Detail |
| --- | --- |
| Document ID | DOC-PP-001 |
| Version | 1.0 |
| Date | April 13, 2026 |
| Author | Ade Maryadi — Owner & Lead Engineer |
| Organization | PT Bima Creative Tech (BCT) |
| Classification | CONFIDENTIAL |
| Status | DRAFT |
| Related Docs | DOC-PC-001 |

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Ade Maryadi |  |  |
| Reviewer |  |  |  |
| Approver |  |  |  |

Table of Contents

Table of Contents	1

1. Phase Timeline	1

2. Resource Allocation	1

3. Key Milestones	1

(Right-click → Update Field in Word)

1. Phase Timeline

| Phase | Weeks | Start | End | Key Deliverables |
| --- | --- | --- | --- | --- |
| 1. Foundation | 8 | Apr 21, 2026 | Jun 13 | Auth+RBAC+Tenant+Spaces+WorkItems+Kanban+Docker+Security |
| 2. Agile Core | 6 | Jun 16 | Jul 25 | Scrum+Backlog+Sprint+Workflow+Reports+PQL |
| 3. Timesheet | 4 | Jul 28 | Aug 21 | Grid+Timer+QuickLog+Approval+Export |
| 4. BIMA AI | 4 | Aug 24 | Sep 18 | FloatingUI+Ollama+NLWorklog+Analysis+SQL |
| 5. Views | 4 | Sep 21 | Oct 16 | Timeline+Calendar+List+Workload+Whiteboard |
| 6. Dashboards | 3 | Oct 19 | Nov 6 | BoD+PO+Landing+CR+Portfolio |
| 7. Docs/Wiki | 3 | Nov 9 | Nov 27 | Wiki+TipTap+Yjs+Versioning |
| 8. AppCatalog | 5 | Dec 1 | Jan 2, 2027 | BRD/FSD/TSD+SemVerDoc+GitHub+AI |
| 9. BudgetPro | 4 | Jan 5 | Jan 30 | Budget+Invoice+eFaktur+Payments |
| 10. WA-Hub | 3 | Feb 2 | Feb 20 | Notifications+Templates |
| 11. SaaS | 4 | Feb 23 | Mar 20 | Branding+Domains+Billing |

2. Resource Allocation

| Role | Phase 1-4 (MVP) | Phase 5-8 | Phase 9-11 |
| --- | --- | --- | --- |
| Lead Engineer (Ade) | 100% | 100% | 100% |
| Contract Backend Dev | 50% | 0% | 50% |
| Contract Frontend Dev | 0% | 50% | 0% |
| QA (automated) | 20% | 30% | 30% |

3. Key Milestones

| Date | Milestone | Gate Criteria |
| --- | --- | --- |
| Jun 13, 2026 | Phase 1 Complete | Auth + Board + Docker working |
| Sep 18, 2026 | MVP LAUNCH | Phase 1-4 complete; 3 internal users |
| Jan 2, 2027 | BETA LAUNCH | Phase 1-8 complete; 3 pilot tenants |
| Mar 20, 2027 | GA LAUNCH | Phase 1-11 complete; public availability |

END OF DOCUMENT — DOC-PP-001 v1.0